## Slide 1
Roadmap for HMIS Improvement in Ethiopia
The Ethiopia HMIS and M&E Strengthening Initiative
Mark H. Spohr, MD
Notes: It is a pleasure and a privilege to be asked to assist Ethiopia with the National HMIS and M&E Strengthening. It is rare to find a country where there is a convergence of leadership, political will and donor support for this important process. Ethiopia has realized the value of a national uniform data set for planning, monitoring and evaluation, and management of health.
The HMIS systems of Ethiopia have been studied repeatedly and found to be inadequate. They are currently fragmented by region and by vertical programs. Donors contribute to the fragmentation with project specific data requirements. There is a lack of data standards and there are conflicting data definitions.
This stakeholder workshop shows that we have high level support for moving forward with an initiative to strengthen HMIS/M&E systems to develop an integrated, standard HMIS system.
Change is always difficult even when everyone agrees on the need for change. We think the advantages of a standardized and simplified core indicator set will be sufficiently compelling to overcome any reservations. The task of national rollout which follows our strengthening initiative will require commitment from all levels of the health care system. We will present the plan for our work and we hope to gain your insight to make it work. We need to know how we can make the initiative attractive to you to gain your full support.
The goal of this workshop is to recruit your support for this initiative for an integrated, standardized HMIS/M&E system. It will only succeed with everyone's support.

## Slide 2
HMIS/M&E Strengthening Initiative Timeplan
Notes: The process of assessment, design, HIS development, and testing will require your input and approval at crucial stages and this is the first of a series of stakeholder workshops that we will be holding during the year. In addition, we have a technical advisory group (TAG) composed of donors, technical experts, and government representatives (Head PPD, HMIS team PPD, Head CSA, Italian cooperation HMIS expert, CDC representative, FMOH Disease Prevention, FMOH Family Health, and other experts as necessary).

## Slide 3
Consensus building
Stakeholder Workshops at important decision points
  Post assessment
  Post design
  Post pilot
Technical Advisory Group
National Advisory Committee

## Slide 4
Assessment

## Slide 5
Levels of Assessment
  National, Regional, and Woreda, and Facility Level
Domains of Assessment
  Data Quality
  Information Use
  Indicators
  Data Handling Process
  Infrastructure - Information and Communication Technology
  Human Resources
Dimensions of Assessment

## Slide 6
Study on best practices from Ethiopia, Africa, and Globally
  Ethiopia regional best practices
  Ethiopia national best practices
  Ethiopia vertical program best practices
  Ethiopia donor, NGO, and project best practices
  Africa best practices
  International best practices
  International standards
Notes: Our approach will be to take the best practices from the Ethiopia regions, Africa, and International experience.
We will design a new system that takes the best and creates an integrated, standards based system.

## Slide 7
System Design
Woreda-centered to Support Integrated Services
  Core Indicator Sets by Level
  Data Design including Data Standards
  Data Flow

## Slide 8
System Development
  Recording and reporting formats
    Registers
    Reporting forms
    Analysis and use of information tools
  Software data entry, communication, and reporting system
    Data entry
    Data communication
    Database
    Decision support system

## Slide 9
National HMIS/M&E Strategy
HMIS/M&E Strategy Document
Human Resource Plan
Information and Communication Technology Development and Deployment Plan

## Slide 10
Implementation Plan
Implementation Strategy
Implementation and Use Guidelines
Training Manuals

## Slide 11
Testing
Pilot Test in 10 Woredas Nationwide
Electronic and paper system
Evaluate pilot and make appropriate changes

## Slide 12
Nationwide Implementation
Beyond the current initiative
Substantial national and regional government effort
Requires coordinated donor support
Use National ICT infrastructure (Woredanet)
Notes: The goal, of course, is nationwide implementation of this system. This will require substantial human resources, training, forms printing and computer and communications resources. Since the HMIS initiative will be ready for nationwide roll out in 12 months, it is not too early to start planning for these resources. This will require a substantial national and regional government effort and will also require coordinated donor support.
Plan for nationwide implementation of the HMIS.
Data warehouse
Use of the National IT infrastructure (Woredanet)>
Additional data sources census, DHS, vital registration, surveys.

## Slide 13
Questions for Groups Discussion
What do you think of the roadmap?
What issues do you see that could be roadblocks?
How do we remove these roadblocks?
Notes: How can we get donors, regions, and FMoH to work together on this initiative?
How can we avoid the waste of resources and duplication of effort from parallel information systems?
How can we get the regions to support and adopt the National HMIS?
How can we recruit resources for scaling up HMIS rollout? (training, hardware, software, communications)
How do we deal with vertical programs? (HIV/AIDS, IDSR, EPI, TB)
How deal with:
Finance
Human Resources
Logistics (Master Plan - UNICEF)
How deal with vertical programs?
demand for their special data, forms, reporting
integration of vertical program data (data warehouse/metadata)

## Slide 14
Coordination
Collaboration
Regional Participation
Donor Support
Woreda-centric information collection and use
Issues