Deliverables list (full duration of project)

| Deliverable No | Deliverable title | Delivery date | Nature | Dissemination level |
| --- | --- | --- | --- | --- |
| D3.1 | Preliminary glacialogical time scales for EDML and EDC ice cores | 12 | R | CO |
| D3.2 | Optimal glacialogical time scales for EDML and EDC ice cores | 36 | R | CO |
| D3.3 | Paleomagnetic records on Southern and Pacific Ocean cores | 24 | R | CO |
| D3.4 | Benthic isotopic records on Southern and Pacific Ocean cores | 24 | R | CO |
| D3.5 | “Ice cores-compatible“ time scales for marine cores | 36 | R | ? |
| D3.6 | SST records (+ sea ice extent by AWI??) for dated marine cores | 36 | R | ? |
| D3.7 | Estimate of the phase between SST and Antarctic air temperature | 36 | R | ? |
| D3.8 | Estimate of the phase between surface ocean and atmospheric 18O | 36 | R | ? |

Work package description (full duration of project)

| Work package number | 3 |  | Start date or starting event: |  |  |  |  | Month 1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant id |  | LSCE (14) |  | BAS (12) | UNIMIB (4) | NP-Tromsoe (10) | UNIBE (11) |  | LGGE (1) | AWI-GEO (3) |
| Person-months per participant |  |  |  | 8 |  |  |  |  |  |  |

Objectives - Synchronisation of EDML and EDC ice cores with other Antarctic ice cores, using layer counting, radio-echo sounding, electrical, chemical and dust records, as well as the signatures of the main volcanic events - Synchronisation of Antarctic and Greenland ice cores using CH4 - Development of an optimal reference ice core time scale for EDML and EDC cores by inverse modelling - Tying the time scales of the marine cores included in this STREP to the reference ice core time scale, based on the correspondence between magnetic properties recorded marine sediments and cosmogenic isotopes fluxes recorded in the ice cores. - Assessment of the phases between the various climatic proxies recorded in the marine and ice cores

Description of work In order to examine the sequence of climatic events and propose mechanisms that could explain the observed climatic variability (WP6), it is crucial to establish the best possible chronologies of the studied climatic time series. This is true for each type of archive, but also when comparing climatic series measured on different archives, such as marine sediments or ice cores. As the purpose of the present STREP is to combine complementary information from marine and ice core records, we first have to build a common time frame for these two types of records. WP3’s aim is hence to prepare consistent chronologies for ice core records and marine records, as a first step towards interpreting and understanding climatic variability (WP6). Ice core chronologies relying on both ice flow modeling and chronological constraints (such as tie points to absolutely dated events or the number of precessional cycles) are the most precise chronologies currently available over the last four climatic cycles. This approach can be extended over the entire length of EDML and EDC cores. In contrast, it is not possible to establish a continuous age model for marine cores because of irregular sedimentation conditions. This is why marine chronologies are obtained by pure orbital tuning and have inherent errors of the order of 3 to 5 ky. We thus propose to develop a reference glaciological time scale using the up to date dating methods and to subsequently tie the marine records onto this time scale. Ice core dating will be performed by the inverse modeling approach using an ice flow model coupled to a firn densification model, as well as chronological constraints on both the ice records (ice 18O and D and gas records (e.g., atmospheric 18O). Synchronization of the different Antarctic ice cores will be done by layer counting, radio-echo sounding, by using electrical, chemical and dust records, and by comparing the signatures of the main volcanic events. Inter-hemispheric synchronization will be achieved through correlation of trace gas records (CH4). The most direct and reliable means of tying the marine records to the ice core records is to correlate the earth magnetic field intensity measured in marine sediments with cosmogenic isotopes fluxes measured in the ice. In addition, in certain Southern Ocean cores magnetic susceptibility mirrors dust records from Antarctic ice cores and can thus be used as a correlative tool. Finally, it has been shown that in some marine cores, benthic foraminifera 18O varies synchronously with Antarctic ice 18O or D records. Therefore, in these cases, benthic 18O can also be used as a correlative tool between marine and ice core records. An immediate output of WP3 will be the assessment of the phase between various marine and ice cores climatic proxies, among others, the phasing between atmospheric 18O and global ocean 18O (provided by WP4), between air temperature above Antarctica and sea surface temperature (SST) at the marine cores locations. Interpretation of these phases will be done in conjunction with WP6.

Deliverables - Preliminary glacialogical time scales for EDML and EDC ice cores - Optimal glacialogical time scales for EDML and EDC ice cores - Paleomagnetic records on Southern Ocean marine cores and one Pacific Ocean core - Benthic isotopic records on Southern Ocean marine cores and one Pacific Ocean core - “Ice cores-compatible“ time scales for marine cores in which it was possible to retrieve magnetic signals or to use other correlation tools between marine and ice core records. - SST records (+ sea ice extent by AWI??) for marine cores aligned on the reference glacialogical time scale - Estimate of the phase between SST at the marine cores locations and Antarctic air temperature - Estimate of the phase between surface ocean and atmospheric 18O

Milestones and expected result - Preliminary glacialogical time scales for EDML and EDC ice cores (month 12) - Optimal glacialogical time scales for EDML and EDC ice cores (month 36) - Investigation of the paleomagnetic properties of the selected deep sea cores; possible selection of other cores if the first ones are found to be inadequate (month 6-12) - Preliminary measurements of benthic isotopes over the last deglaciation on the Pacific core (month 18), verification of the relationship between benthic isotopes and ice D or 18O records - Measurements of SST (+ sea ice extent by AWI??) on selected Southern Ocean cores (Month 36) - Completion of marine isotopic and SST records (month 36) - Estimate of the phase between SST at the marine cores locations and Antarctic air temperature (month 36) - Estimate of the phase between surface ocean 18O and atmospheric 18O (month 36)

Deliverable numbers in order of delivery dates: D1 – Dn

Month in which the deliverables will be available. Month 0 marking the start of the project, and all delivery dates being relative to this start date.

Please indicate the nature of the deliverable using one of the following codes:

R = Report

P = Prototype

D = Demonstrator

O = Other

Please indicate the dissemination level using one of the following codes:

PU = Public

PP = Restricted to other programme participants (including the Commission Services).

RE = Restricted to a group specified by the consortium (including the Commission Services).

CO = Confidential, only for members of the consortium (including the Commission Services).

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.