## Phase 1
DATE:
Rec # | % Done | Action / Task Name | Hub Owner | Gerber Owner | Deadline | Start | Finish | Comments
General
P1G1 | 50% | Validate meeting notes | Shelley | GSP - Don, Brian | 2002-09-19 | 2002-09-13 |  | Brian - complete 9/19
P1G2 | 100% | Determine 1st phase facility | Hub Group Boston | GSI | 2002-09-13 | 2002-09-11 | 2002-09-12
P1G3 | 100% | Clearly define staffing needs by facility (on site, call center) | Richard | GS- Ronald | 2002-09-20 | 2002-09-01 | 2002-09-19 | discussed on 9/18 conf. Call
P1G4 | 100% | Customer and vendor Master files | Tom L | GSI - Pam | 2002-09-15 | 2002-09-01 | 2002-09-13 | received for GT and GSP
P1G5 | 50% | List of Gerber employees who need access to Customer Advantage | Shelley | GSI - Colette | 2002-09-15 | 2002-09-11 |  | Initial list has access to Customer Advantage
P1G6 | 0% | Determine initial trigger point for sending order information electronically | Shelley | GSI - Don, Jochen | 2002-09-20 | 2002-09-01 |  | began to work on with Pilot shipment flow charts
P1G7 | 100% | Determine which number will be used to identify shipments | Shelley | GSI - Don, Jochen | 2002-09-20 | 2002-09-01
P1G8 | 0% | Determine what level of detail will be transmitted with orders | Shelley | GSI - Colette | 2002-09-20 | 2002-09-01
P1G9 | 0% | send test orders via EDI | Tom L | GSI - Pam | tbd | tbd |  | dependent on establishing trigger points
P1G10 | 100% | Provide Mike Bonosconi with desk space in CT | Mike | GSI | 2002-09-20 | 2002-09-16 | 2002-09-25 | emailed Colette 9/20
P1G11 | 25% | Determine Preliminary Reporting requirements | Shelley | GS- Ronald | 2002-09-20 | 2002-09-16 |  | emailed Ronald 9/20
P1G12 | 50% | Validate Project Scope | Shelley | GS- Ronald | 2002-09-20 | 2002-09-16 |  | emailed Ronald 9/18
P1G13 | 0% | Validate invoicing requirements as of 10/1 | Shelley | GS- Ronald | 2002-09-25 | 2002-09-16
P1G14 | 0% | Finalize Reporting Requirements | Shelley | GS- Ronald | 2002-09-24 | 2002-09-20
P1G15 | 0% | Test and validate reports | Shelley | GS- Ronald | 2002-09-27 | 2002-09-24
P1G16 | 0% | Test and validate load plans | Shelley | GSP - Don, Brian | 2002-09-27
P1G17 | 0% | Test and validate load plans | Shelley | GT - Jochen | 2002-09-27
Operations
P1O1 | 0% | send orders viaTV sheet prior to 10/1 | Mike | GSP - Don, Brian | 2002-09-30 | 2002-09-04
P1O2 | 75% | send orders viaTV sheet prior to 10/1 | Mike | GT - Jochen | 2002-09-30 | 2002-09-04
P1O3 | 0% | Develop and publish operational communication plan | Mike |  | 2002-09-20 | 2002-09-17

## Priority
ADs | Priority | Selected
Polisea | Low | Software Accumark
Gregorcic | Mid | Software AccuNest
Glengo | High | Software V-STITCHER
Software WEBPDM
PnP Digitizer
PnP SP Plotter
PnP Plotter Accuplot 100
PnP Plotter Accuplot 3xx
PnP XLP Plotter
PnP INFINITY
SPC Taurus
SPC DCS
SPC Z1
MPC Cutter 32xx
MPC Cutter 52xx
MPC Cutter 72xx
MPC Cutter GTXL
MPC GT 1000
MPC S-93-5
MPC S-93-7
MPC S-91
MPC XLC-7000
MPC Z7
SPR Single Ply Feeder
SPR Spreader SYN
SPR Spreader XLs
SPR Spreader 250s
NON Gerber

## Open
Notification Date | ADs' | Escalation # | Equipment list: Drop down window to select equipment | Customer | Problem description | Priority: Drop down list | Product Application Indication | Closing date
2014-07-07 | Name | 16 | Accumark | ADILISIK | They are working Accumark V8.5 with SQL storage area. They want to do that, maker user can not change pieces data. And also model maker person are not change any maker in system. We would like to set permision of accumak system in sql manager from Accumark System. But The Accumak systems does not read with the Maker read and piece read permission in UserPerm table.And also I check that I set up these permission using SSDE SQL Manager. Could you confirme that the permission in accumark system is still working V8.5 and V9? The system is SQL server 2008 R2 10.50.2500. All users are sysadim and public in SQL Server | Mid
2014-07-07 | Name | 17 | Accumark | TAHA | Digitizer Configration not able between Accumark V8 and Accumark V9 system. We set the digit Xlp at Accumark V9 with DIGITIZEDIVE option,other Accumark V8 system is not set digit parameters. (exam: Digit folder, Rule Table etc.). If we set digit at Accumark V8 system, Accumark V9 system does not set digit parameter. | Mid
2014-07-20 | Name | 18 | Accumark | ARMINE | The System is occured time fix error . Please send us timefix.lic file for 44209 you will find installlic screenshut | High
| Name | 19
| Name | 20
| Name | 21
| Name | 22
| Name | 23
| Name | 24
| Name | 25
| Name | 26
| Name | 27
| Name | 28
| Name | 29
| Name | 30
| Name | 31
| Name | 32
| Name | 33
| Name | 34
| Name | 35
| Name | 36
| Name | 37
| Name | 38
| Name | 39
| Name | 40
| Name | 41
| Name | 42
| Name | 43
| Name | 44
| Name | 45
| Name | 46
| Name | 47
| Name | 48
| Name | 49
| Name | 50
| Name | 51
| Name | 52
| Name | 53
| Name | 54
| Name | 55
| Name | 56
| Name | 57
| Name | 58
| Name | 59
| Name | 60
| Name | 61
| Name | 62
| Name | 63
| Name | 64
| Name | 65
| Name | 66
| Name | 67
| Name | 68
| Name | 69
| Name | 70
| Name | 71
| Name | 72
| Name | 73
| Name | 74
| Name | 75
| Name | 76
| Name | 77
| Name | 78
| Name | 79
| Name | 80
| Name | 81
| Name | 82
| Name | 83
| Name | 84
| Name | 85
| Name | 86
| Name | 87
| Name | 88
| Name | 89
| Name | 90
| Name | 91
| Name | 92
| Name | 93
| Name | 94
| Name | 95
| Name | 96
| Name | 97
| Name | 98
| Name | 99

## Closed
Notification Date | ADs' | Escalation # | Equipment list: Drop down window to select equipment | Customer | Problem description | Priority: Drop down list | Product Application Indication | Closing date
2013-05-13 | Name | 1 | Software Accumark | OZON TEXLINE | IT Departmen Change the time in nps server in weekend. And Same of accumak system is occurred Time Tamper error. Could you send me timefix. IT Departmen Change the time in nps server in weekend. And Same of accumak system is occurred Time Tamper error. Could you send me timefix files of 53995, 53997.54000,54001,540002,53996,53998,53994. You will find installlic screen shuts in attachment. | High | May 13th 2013: Send the timefix license for the keys: #53995, #53997, #54000, #54002, #53996, #53998, #53994. They should foolow these instructions to apply the Time Tamper License. 1. Do not delay applying the timefix.lic. The TIMEFIX.LIC is created to run on one specific date. *** Do not use the desktop Install License icon to apply the Time Tamper license. ***. 2. Make sure the system clock is set to the correct time. 3. Save the attached files to a temporary directory, such as C:\TEMP. 4. Using Windows Explorer, browse to the temporary directory, rename clean.zib to clean.zip, and extract (unzip) the clean.zip file. Be sure to extract it to the current directory. 5. On Windows XP, log in as Administrator, then open a command promt. On Windows 7, open a command prompt with Administrator rights by selecting the icon under Accessories and right click Run As Administrator. 6. Change to to the temporary directory by using the CD \TEMP command. 7. At the command prompt, type LSCLEAN.EXE TIMEFIX.LIC. 8. The message "Please refer to CLEAN.LOG for details" will appear. The Time Tamper is now corrected. 9. If you received a new license to replace an expired license, install the new license by using the Install License icon on the desktop.
2013-05-13 | Name | 2 | Software Accumark | REYHAN | SomePiece in System is occured error and Accumark System does not read these piece and occured error. I send Program Reports file in attachment and ScreenShut. We test the file other accumark system but same problem occured with same piece. | Mid
2013-05-14 | glengo | 3 | Software Accumark | ALMATY | Answer for Technical Escalition #13. The timefix file occued error message “LSClean license execution is exhausted.” in CLEAN.LOG. I check the file its workin until 17 May. Could you send me new timefix.lic file for today. You will find Program reports file in attachment.Accumark version is 8.4.1
2013-10-02 | glengo | 4 | Software Accumark | OMENT | The System is occured time temper error. You will find Installlic Application screen shot in attachment in the email. Please send us timefix.lic file for 42218 until 3th Oct 2013
2013-10-10 | glengo | 5 | XP licance CD of XLc7000 | general | all dell computers of XLc7000s come with Windows7 licance but Cutworks program works on XP licance. However Gerber does not send XP licance CD of Dell computers. Wen computers need format we can not do it and we use crack XP. This couse serious problem with the customers.
2013-12-19 | glengo | 6 | software accumark | Lokay Tekstil | The System is occured time temper error. . Please send us timefix.lic file for 40215 -8,5 AE URGENTLY |  |  | 2013-12-20
2013-12-24 | glengo | 7 | software accumark | Dayteks | The System is occured time fix error . Please send us timefix.lic file for 41456 -8,4 URGENTLY |  | timefix sent to Ufuk, 27 December, 9 AM | 2013-12-27
2013-12-27 | glengo | 8 | software accumark | balinler | The System is occured time fix error . Please send us timefix.lic file for 42212 -8,4 URGENTLY |  |  | 2013-12-30
2013-12-30 | glengo | 9 | software accumark |  | Accumark system is occured 918 error code. You will find in attachment PERU.log file. How do we fix? | High | solved by glengo. Computer time changed | 2013-12-30
2014-01-28 | glengo | 10 | Software Accumark | rimaks | The System is occured time fix error . Please send us timefix.lic file for 48813 and 48811 URGENTLY |  | 28-02-2014Gbrandl:send e-mail to GTElicense send to Glengo | 2014-01-28
2014-01-29 | glengo | 11 | software accumark | rimaks | The System is occured time fix error . Please send us timefix.lic file for 48870,49258,53063, 49304,23767,47871,42601,40271,48758,48762 URGENTLY |  | Gbrandl 29-01-2014 send to GTElicense. And sent dot Glengo 13:10 | 2014-01-29
2014-05-02 | glengo | 13 | software accumark | gizia | The System is occured time fix error . Please send us timefix.lic file for 22214 URGENTLY |  |  | 2014-05-02
2014-02-21 | glengo | 12 | software accumark | taha | The System is occured time fix error . Please send us timefix.lic file for 37493 URGENTLY
2014-05-23 | glengo | 14 | software accumark | general | when plot dosfile for the mirror parts is created in PDS Accumark 8.5 and/or 9.0 for cutting plotters like SP200 and some other brands , the sewing lines in the dosfile are created twice and cutting plotters plot the sewing lines twice causing time waste. you may see it in the attached file.
2014-06-10 | Name | 15 | Accumark | UNITEKS | The System is occured time fix error . Please send us timefix.lic file for 50377 you will find install URGENTLY | High
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name
Name